## Sheet1
Website |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
|  |  | 25.11 | 26.11 | 27.11 | 28.11 | 29.11 | 30.11 | 1.12 | 2.12 | 3.12 | 4.12 | 5.12 | 5.12 | 7.12 | 8.12 | 9.12 | 10.12 | 11.12 | 12.12 | 13.12 | 14.12 | 15.12 | 16.12 | 17.12 | 18.12 | 19.12 | 20.12 | 21.12 | 22.12
Planning |  | 3d | bar: Week 1 M to Week 1 W
Kick off meeting client and team | Project manager | 0.5 | bar: Week 1 M
Style sheet | Design | 1.5d | bar: Week 1 M to Week 1 T
Site archytecture & wireframes | Front- end | 1.5d | bar: Week 1 M to Week 1 T
Meetings | bar: Week 1 M; Week 1 TH; Week 2 T; Week 2 F; Week 3 F; Week 4 SA
| 1th presentation at customer | Project manager | Week 1 M: 0.5d
| Briefing the team feedback customer | Entire team | Week 1 M: 0.5d
| Gathering more info for payment and delivery page | Project manager | bar: Week 1 M; Week 2 T
| Present first 3 pages to customer | Project manager | Week 1 M: 0.5d
| Briefing team feedback customers | Everyone | Week 1 M: 0.5d
| Update client on progress | Project manager | Week 1 M: 0.5d
| Presenting & handover website | Project manager | Week 1 M: 0.5d
| Build |  | Week 1 M: 17.5d
| Adjust wireframes & site archytechture | Front-end | Week 1 M: 1.5d
| Navigation & footer | Front- end | bar: Week 1 M; Week 1 SA
| Homepage | Front- end | bar: Week 1 M; Week 2 T
| Product page | Front- end | bar: Week 1 M; Week 2 W
| Product process page | Front- end | bar: Week 1 M; Week 2 TH
| Adjust after customer feedback | Front- end | bar: Week 1 M; Week 2 F
| Order page | Front- end | bar: Week 1 M; Week 2 SA
| About page | Front- end | bar: Week 1 M; Week 3 T
| Delivery page | Front- end | bar: Week 1 M; Week 3 W
| Payment page | Front- end | bar: Week 1 M; Week 3 TH
| Contact page | Front- end | bar: Week 1 M; Week 3 F
| Terms and conditions page | Front- end | bar: Week 1 M; Week 3 SA
| Login & register | Front- end | bar: Week 1 M; Week 4 T
| Saving preferences when logged in | Front- end | bar: Week 1 M; Week 4 W
| Testing & adjusting | Front- end | bar: Week 1 M; Week 4 TH to Week 4 F
| Design |  | Week 1 M: 9.5d
| Adjust stylsheet to feedback | Graph designer | Week 1 M: 1.5d
| homepage | Graph designer | bar: Week 1 M; Week 1 SA
| product page | Graph designer | bar: Week 1 M; Week 2 T
| product process page | Graph designer | bar: Week 1 M; Week 2 W
| Order page | Graph designer | bar: Week 1 M; Week 2 TH
| Adjust after customer feedback | Graph designer | bar: Week 1 M; Week 2 F
| About page | Graph designer | bar: Week 1 M; Week 2 SA
| Delivery & payment page | Graph designer | bar: Week 1 M; Week 3 T
| Contact & terms and conditions page | Graph designer | bar: Week 1 M; Week 3 W
| Content |  | Week 1 M: 12d
| Research products/ product process/ about page | Copywriter | bar: Week 1 M to Week 1 W
| Write homepage & product page | Copywriter | bar: Week 1 M; Week 1 TH to Week 1 F
| Write product process page | Copywriter | bar: Week 1 M; Week 1 SA
| Write order and about page | Copywriter | bar: Week 1 M; Week 2 T to Week 2 W
| Write delivery & payment page | Copywriter | bar: Week 1 M; Week 2 TH; Week 2 SA
| Adjust to feedback customer | Copywriter | bar: Week 1 M; Week 2 F
| Write contact & terms and conditions page | Copywriter | bar: Week 1 M; Week 3 T to Week 3 W
Photography | bar: Week 1 M; Week 1 TH to Week 1 SA; Week 2 T to Week 2 F
| Pictures product page | Photograph | bar: Week 1 M; Week 1 TH to Week 1 F
| Pictures product process | Photograph | bar: Week 1 M; Week 1 SA; Week 2 T
| Pictures about page | Photograph | bar: Week 1 M; Week 2 W to Week 2 TH
| Adjust to feedback customer | Photograph | bar: Week 1 M; Week 2 F